## Cover
UAT- Defect Report: Business Site
Created By | Sayan Basak | Date | 2024-02-01
Reviewed by | Anirban Chakrabarty | Date | 2024-02-02
Approved By | Debasish Nath | Date | 2024-02-03

## UAT Defects
SL # | Reporting Date | Feature | Bug Description | Priority | Status | Closure Date | Reproduction Steps | Notes | Image
1 | 2024-02-01 | Page Header | The favicon / "anodiam" logo of the browser tab is not a transparent png. Four corners of the logo show white pixels. | 4 | Open |  | 1. Visit: https://sites.google.com/view/anodiam 2. Watch the brower tab's header. | A transparent png file named "Web Tab Logo.png" has been already emailed to Anttech for the purpose of usage in this favicon / logo. This .png file will be emailed again. Screen shot attached in file: "DefectImages.docx": Image-1.
2 | 2024-02-01 | Page Header | The browser tab header reads "Home" for home page. It should read "Anodiam" for Home page. | 4 | Open |  | 1. Visit: https://sites.google.com/view/anodiam 2. Watch the brower tab's header. | Screen shot attached in file: "DefectImages.docx": Image-1.
3 | 2024-02-01 | Page Header | The Main icon of the website is not proper | 5 | Open |  | 1. Visit: https://sites.google.com/view/anodiam | The Icon of the website should be the Image-3 from file: "DefectImages.docx" and NOT Image-2. The catch line at the bottom of Image-2 is not clearly readable. Screen shot attached in file: "DefectImages.docx": Image-3.
4 | 2024-02-01 | Page Header | Menu names to be changed. We need only four pages: 1> Home 2> Featured Courses 3> Free Materials 4> Contact Us | 5 | Open |  | 1. Visit: https://sites.google.com/view/anodiam | Anodiam's business site needs only four of the following pages: 1> Home 2> Featured Courses 3> Free Materials 4> Contact Us
5 | 2024-02-01 | Page Header | The color of the menu bar should be Dark Blue (RGB = 2, 60, 97), not black or the existing color | 3 | Open |  | 1. Visit: https://sites.google.com/view/anodiam | Screen shot attached in file: "DefectImages.docx": Image-4.
6 | 2024-02-01 | Home Page: Page Header | The word anodiam should be removed from the header. We will give you a new background image. N.B. – The replacement image will be mailed. | 5 | Open |  | 1. Visit: https://sites.google.com/view/anodiam
7 | 2024-02-02 | Home Page: Body | Delete the section as it is not required. | 5 | Open |  | 1. Visit: https://sites.google.com/view/anodiam