## Cover
UAT- Defect Report: Business Site
Created By | Sayan Basak | Date | 2024-02-01
Reviewed by | Anirban Chakrabarty | Date | 2024-02-02
Approved By | Debasish Nath | Date | 2024-02-03

## UAT Defects
SL # | Reporting Date | Com | Bug Description | Priority | Status | Closure Date | Reproduction Steps | Notes | Image
1 | 2024-02-01 | Free Materials: Content | Contents should show Brand Ambassador and CEO's videos. | 5 | Closed | 2024-02-21 | 1. Visit: https://sites.google.com/view/anodiam 2. Go to Galley page.
2 | 2024-02-09 | All Pages -Cards | Horizontal Margin 5px for texts of all cards to be incorporated | 5 | Closed | 2024-02-21
3 | 2024-02-09 | Courses | Include cards for all courses at classplus app of Anodiam | 5 | Closed | 2024-02-21
4 | 2024-02-09 | Classplus App | Create Thumbnails for all courses at classplus app of Anodiam | 5 | Closed | 2024-02-21