## Tracker
SlNo | Item Description | Type | Owned by | Priority | Status | Comments | Link
1 | Plan School and College Visits | Marketing | Rahul | 5 | WIP | Pending on Anttech business site
2 | Google Anttech Google business site | Marketing | Sayan | 5 | WIP
3 | Update profitability sheet with AI course Values | Marketing | Debashish | 5 | WIP
5 | February Accounts | Ops | Anirban | 5 | Todo
6 | Create generic Thumbnail (Coverpage) image / ppt for courses | Ops | Sayan | 4 | WIP
7 | AI Internal Classes - Sayan | Ops | Sayan | 4 | WIP | Start from 5-Feb-2024
8 | Communication - Internal Classes | Ops | Rahul | 4 | WIP
9 | AI Internal Classes by Anirban | Ops | Anirban | 4 | WIP | Start from 4-Jan-2024
10 | Publish AI course materials on Anodiam platform | Ops | Sayan | 4 | WIP
11 | Create a detailed syllabus for communication | Marketing | Rahul | 4 | WIP
12 | CRM calls: Just dial to Urban Pro: | CRM | Rahul | 3 | WIP | Check Just Dial daily. Transfer to Urban Pro. Just Dial email Id : kolkata@justdial.com. After 5th Feb.
13 | Reel Plan (AI Ad) | Marketing | Anirban | 3 | Todo | Need to break this down further
14 | Reel Plan (Generic Ad) | Marketing | Anirban | 3 | Todo | Need to break this down further
15 | Start / config Selenium batch for Ashmita / Pranay | Ops | Rahul | 3 | WIP | Pranay has been updated.
16 | News Paper flyers distribution | Marketing | Rahul | 2 | WIP | To start in Feb 4th week
17 | Publish purchased course materials on Anodiam platform | Ops | Anirban | 1 | WIP

## Proposal email
SlNo | Item Description | Type | Owned by
1 | Omit the Free word from everywhere | Marketing | Sayan
2 | Shorten the body of emails | Marketing | Sayan
3 | Write full names of institutions | Marketing | Sayan

## Antech-Issues
SlNo | Item Description | Type | Owned by | Priority | Status | Comments
1 | Get some 5 star reviews | Marketing | Sayan | 5 | WIP
2 | On pressing Website button the page should redirect to google.anodiam.mybusiness.site | Marketing | Sayan | 5 | Todo
3 | Search strings to be given to Anttech: NEET IIT institute in Kolkata - AI courses in Kolkata - IT Courses in Kolkata | Marketing | Sayan | 5 | Todo
4 | Images & Logos | Marketing | Sayan | 5 | WIP
5 | Videos, Youtube content. Create an youtube channel and start putting in our contents | Marketing | Sayan | 5 | Todo
6 | About Us & Service should have AI Professional & IT | Marketing | Sayan | 5 | Todo
7 | About Us & Service should have NEET & IIT JEE etc (Others) | Marketing | Sayan | 5 | Todo
8 | Ensure we have a label for the button to to open anodiam app if it is already installed (or download app if not installed) | Marketing | Sayan | 5 | Todo
9 | Test the responsiveness of https://www.google.business.sample.site | Marketing | Sayan | 5 | Done
10 | Must have a Login button "Visit anodiam.com website": upon clicking it will open anodiam.com >> classplus/YOWWA website | Marketing | Sayan | 5 | Todo
11 | Put a transparent png of Anodiam small logo for the browser tab header. White borders should not show | Marketing | Sayan | 5 | Todo
12 | Logo at top left to be changed | Marketing | Sayan | 5 | Todo
13 | Home page header label to be blank. Header image to contain the big logo | Marketing | Sayan | 5 | Todo
14 | Main header should be consistant (Camel case, Oxygen font, Not bold, size = size of "About Us") | Marketing | Sayan | 5 | Todo
15 | Headings of all pages should have Different Images | Marketing | Sayan | 5 | Todo
16 | \'Anodiam' word to be written on the top left label of each page | Marketing | Sayan | 5 | Todo
17 | Orange Header instead of black, while scrolling down | Marketing | Sayan | 5 | Todo