## Tracker
SlNo | Item Description | Type | Owned by | Priority | Status | Comments | Link
1 | Plan School and College Visits | Marketing | Rahul | 5 | WIP | Pending on Anttech business site, Email body shortened and rectified, Institution Full name left
2 | Resize invitation Email | Marketing | Debashish | 5 | WIP
3 | Institution full name to be listed | Marketing | Rahul | 5 | WIP
5 | Close UAT Defects of Anodiam Business Site | Ops | Sayan | 5 | WIP | Dependency on youtube videos, Cover page for class plus courses
6 | Make scripts for 5 star google reviews | Marketing | Rahul | 5 | Todo | Make scripts for 5 star google reviews
7 | Get some 5 star reviews | Marketing | Debashish | 5 | WIP | Collect 5-6 actual reviews from Santanu, Avishek, Sahista, Pratyay Kayali, Pritam, Sayan, Bappa, Ananya, Debasish Sir, Rahul
8 | Search strings to be given to Anttech: NEET IIT institute in Kolkata - AI courses in Kolkata - IT Courses in Kolkata | Marketing | Sayan | 5 | Todo
9 | Create an youtube channel | Marketing | Ananya | 5 | Todo
10 | Create Videos & Youtube content. Start putting in our Youtube channel | Marketing | Anirban | 5 | Todo
11 | Create Subdomain for login into classplus app | Marketing | Anirban | 5 | Todo
12 | Download Anttech business site source code and upload it to anodiam.com domain | Marketing | Debashish | 5 | Todo
13 | Create generic Thumbnail (Coverpage) image / ppt for courses | Ops | Sayan | 4 | WIP
14 | AI Internal Classes - Sayan | Ops | Sayan | 4 | WIP | Start from 5-Feb-2024
15 | Communication - Internal Classes | Ops | Rahul | 4 | WIP | Plan the table of contents for the syllabus
16 | AI Internal Classes by Anirban | Ops | Anirban | 4 | WIP | Start from 4-Jan-2024
17 | Publish AI course materials on Anodiam platform | Ops | Sayan | 4 | WIP | PPTs only for now at version 0.0.1.
18 | Publish Java course materials on Anodiam platform | Ops | Debashish | 4 | WIP | PPTs only for now at version 0.0.1. Debasish da to work on Java Materials. Add slides for Advanced Java & MySQL etc. in next versions
19 | Create a detailed syllabus for communication | Marketing | Rahul | 4 | WIP | To be finished by 15-Feb
20 | CRM calls: Just dial to Urban Pro: | CRM | Rahul | 3 | WIP | Check Just Dial daily. Transfer to Urban Pro. Just Dial email Id : kolkata@justdial.com. After 5th Feb.
21 | Write email to stop just dial | CRM | Anirban | 5 | Todo
22 | Reel Plan (AI Ad) | Marketing | Anirban | 3 | Todo | Need to break this down further
23 | Reel Plan (Generic Ad) | Marketing | Anirban | 3 | Todo | Need to break this down further
24 | Start / config Selenium batch for Ashmita / Pranay | Ops | Rahul | 3 | WIP | Pranay has been updated.
25 | News Paper flyers distribution | Marketing | Rahul | 2 | WIP | To start in Feb 4th week