## Tracker
Item Number | Item Description | Type | Owned by | Priority | Status | Comments | Link
1 | Plan School Visits | Marketing | Rahul | 5 | WIP
2 | Plan College Visits | Marketing | Sayan | 5 | WIP
3 | CRM calls | CRM | Rahul | 5 | WIP
4 | Reel Plan (Generic Ad) | Digital Marketing | Anirban | 3 | WIP | Need to break this down further
5 | Reel Plan (AI Ad) | Digital Marketing | Anirban | 3 | WIP | Need to break this down further
6 | Google Anttech Photoshhot | Digital Marketing | Sayan | 5 | Todo | Need to Plan
7 | Google Anttech Google business site | Digital Marketing | Debashish | 5 | WIP | Ask Anttech to give us a sample of an existing / running https://www.google.business.sample.site Design the corresponding pages & components for https://www.google.business.anodiam.site Test the responsiveness of https://www.google.business.sample.site
8 | anodiam.com website | Digital Marketing | Debashish | 5 | Todo | First cut to be discussed
9 | Integration with Class plus website / app login | Digital Marketing | Debashish | 5 | Todo | Ask Classplus about the URL / hyperlink for anodiam web app login / register
10 | Student fees collection report for December | Ops | Anirban | 5 | WIP | Anirban has to send bank receipt
11 | Conduct Internal Assessment Test Chem - Avishek - Nov | Ops | Debashish | 5 | WIP | Avishek to complete correction by 30-Dec-2023
12 | Conduct Internal Assessment Test Physics - Avishek - Dec | Ops | Debashish | 5 | WIP | Exam to be conducted on 30-Dec-2023
13 | Conduct Internal Assessment Test Maths - Avishek - Dec | Ops | Debashish | 5 | WIP | Exam to be conducted on 30-Dec-2023
14 | Company Income Expense Ledger & Balance Sheet | Ops | Anirban | 5 | Todo | Start in December
15 | College doors app defect management | Mock Test | Debashish | 3 | WIP | Anirban to have a walkthrough
16 | Start / config Selenium batch for Ashmita / Pranay | Ops | Debashish | 5 | Todo
17 | News Paper flyers distribution | Marketing | Rahul | 2 | WIP | To start in Feb 4th week
18 | Batch start for Priyangsu Giri BBA Sem 1 | Ops | Debashish | 5 | WIP | Need to send email to Anupam sir

## MockTest
23 | Mock test Dry run | Mock Test | Debashish | Todo | Final Dry Run by
24 | Mock Test Question Paper | Mock Test | Rahul | Todo | Debashish To Help in technology, Rahul to download & curate soft copies of question bank
25 | Mock Test Presentation | Mock Test | Rahul | Todo | Debashish To Help
26 | Mock test schedule | Mock Test | Anirban | WIP | Monday EOD
20 | Flow chart for Mock Test | Mock Test | Ananya | WIP | by 28/11/2023
21 | Scanned PDF for Mock test, Waqr to confirm | Mock Test | Rahul | Todo | by 28/11/2023
28 | What will be the exact tests (class, board, subjects) for the incumbent / interested students? | Mock Test
29 | Is schedule ready for all the prospective students according to their class / board / subjects? | Mock Test
30 | Who will be the faculty for each test on each date and time? (Get consent from the faculty on availability) | Mock Test
31 | Who will lead the team on each day and each test? | Mock Test
32 | What team members will be supporting the tests for admin work? Who will do what? | Mock Test
33 | What team members will be supporting the tests for Marketing work / presentation? Who will do what? | Mock Test
34 | Is faculty ready with demo class? How will faculty raise interest of the students on the topic of her/his demo class. Will the question paper pattern be hard for these chapters? | Mock Test
35 | Does faculty have soft copies of class notes / presentations / points to remember / sample questions etc. to be displayed in the demo class? | Mock Test
36 | Can the faculty / team show the apps (class plus / college doors) as points of competencies during the presentation after mock test? | Mock Test
37 | Is the demo class rehearsed? | Mock Test
38 | Is the marketing / counselling / presentation rehearsed? | Mock Test
39 | What is the question paper pattern for the test as per board / class/ subject? (Time limit, number of questions , full marks, marks per question / sections, questions covering entire syllabus, question type (MCQ, objective, descriptive etc) | Mock Test
40 | Is the question paper reviewed? | Mock Test
41 | Do we have answering instructions / sample answers ready? | Mock Test
42 | Wich chapters will students will find easy / scoring, which ones difficult? Are we designing demo class around the critical ones? | Mock Test
43 | Is each team member aware of all the above points? | Mock Test
44 | what will be the start time and end time of tests? | Mock Test
45 | Which room will the students sit? | Mock Test
46 | Which room will the parents sit? | Mock Test
47 | Which toilet, water dispenser, facilities, parking, tea coffee etc… | Mock Test
48 | Where will other BAU go during Mock tests? | Mock Test
49 | How we manage invigilation? | Mock Test
50 | How we manage parent's expectation? | Mock Test
51 | Will the parents attend demo class? | Mock Test
52 | Will counselling be in groups or individual? | Mock Test
53 | Is counselling strategy defined? | Mock Test
54 | What will be the course fees for each subject / board / test? Will we provide discounts? Is this as per profitability? | Mock Test
55 | Which faculty will be appointed for each students upon enrollment? Is that faculty aware? Is she the same one conducting the test? | Mock Test
56 | How do we manage expectations and volatile / unrully behavior of students and parents? Are team members aware of all these? | Mock Test
57 | How do we invite students for the consecutive mock tests? | Mock Test
58 | How do we show them a career path for individual students during counselling? | Mock Test
59 | How do we ensure all students / parents / faculty and team members leave in a positive note? | Mock Test
60 | Are we aware of App functionalityies for each test? | Mock Test
61 | Will the students get question papers on laptops / mibile phones? Or papers? If online, did we ask them to bring laptops / mobiles? Will we give them wifi access? | Mock Test
62 | If tests are online how do we manage disruptions due to FB and other websites on the same device? | Mock Test
63 | How we collect phone numbers and contact info of parents / students? | Mock Test
64 | How do we manage CRM with each one after mock tests? | Mock Test
65 | Are we ready with a ppt about Anodiam and why they enroll with us? Who will deliver the presentation? When? Is it reharsed? | Mock Test
66 | Do we ask clients to join a FB / WA group? Is that group a generic one or something specific for particular subject / board / class? | Mock Test
67 | How do we cross sale other subjects to them? How do we ask them to refer other students? How do we ask them to do AI and Communication classes? | Mock Test
69 | will we send street directions / locations to the parents? Will they assemble 15 mins early? | Mock Test
70 | Will we put up internal branding during mock test (Standies / leaflets)? | Mock Test
71 | Will ge need signages inside the building? | Mock Test
72 | Seating arrangements? | Mock Test
73 | Cleaning services and housekeeping? | Mock Test
74 | Define a sequence / timeline of key activities for mock test | Mock Test
75 | Dry run a mock test end to end as per the above equence / timeline of key activities | Mock Test

## WorkDays
Names | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Day | In Time | Out Time
Anirban Chakrabarty | Working | Working | Working | Working | Working | Working | Working | Monday | 10:00 | 18:00
Debasish Nath | Working | Working | Off | Working | Working | Working | Working | Tuesday | 10:00 | 18:00
Ananya Moitra | Working | Working | Working | Working | Working | Working | Working | Wednesday | Off Day
Rahul Dutta | Working | Working | Off | Working | Working | Off | Working | Thursday | 10:00 | 18:00
Shayan Basak | Off | Working | Working | Working | Working | Off | Off | Friday | 10:00 | 16:00
[8 empty] | Saturday | 10:00 | 16:00
[8 empty] | Sunday | 10:00 | 18:00