## Tracker
SlNo | Item Description | Type | Owned by | Priority | Status | Comments | Link
1 | Plan School Visits | Marketing | Rahul | 5 | Todo
2 | Plan College Visits | Marketing | Rahul | 5 | WIP
3 | Google calander Training for team | Marketing | Sayan | 5 | Todo
4 | Training to Create Gmail groups | Marketing | Sayan | 5 | WIP
5 | Create events at meetup app or https://www.townscript.com/ or FB Events | Marketing | Sayan | 5 | Todo
6 | Google Anttech Queries | Marketing | Sayan | 5 | WIP | We need to call Anttech to resolve issues
7 | Google Anttech Google business site | Marketing | Debashish | 5 | WIP | Anttech will deliver website on 30th Jan 2024.
8 | Publish purchased course materials on Anodiam platform | Ops | Debashish | 4 | WIP | Uploaded course materials of Maths and Science for Std VIII. Maths & Biology for Std IX.
9 | Publish AI course materials on Anodiam platform | Ops | Sayan | 4 | WIP
10 | AI Internal Classes - Sayan | Ops | Sayan | 4 | WIP | Start from 11-Jan-2024
11 | AI Internal Classes by Anirban | Ops | Anirban | 4 | WIP | Start from 4-Jan-2024
12 | Create generic Thumbnail (Coverpage) image / ppt for courses | Ops | Sayan | 4 | Todo
13 | CRM calls: Just dial to Urban Pro: | CRM | Rahul | 3 | WIP | Check Just Dial daily. Transfer to Urban Pro. Just Dial email Id : kolkata@justdial.com
14 | Conduct Internal Assessment Test BBA | Ops | Debashish | 3 | WIP | Test to be conducted on 29-Jan-2024
15 | Need Bank A/c # & IFSC for Rahul to generate payslip | Ops | Rahul | 3 | WIP | Urgent requirement as it is pending for nearly 7 days.
16 | Reel Plan (AI Ad) | Marketing | Anirban | 3 | Todo | Need to break this down further
17 | Reel Plan (Generic Ad) | Marketing | Anirban | 3 | Todo | Need to break this down further
18 | Start / config Selenium batch for Ashmita / Pranay | Ops | Rahul | 3 | WIP | Pranay has been updated.
19 | News Paper flyers distribution | Marketing | Rahul | 2 | WIP | To start in Feb 4th week
20 | Company Income Expense Ledger & Balance Sheet | Ops | Anirban | 3 | Done | Start in December
21 | Student fees collection report for December | Ops | Anirban | 5 | Done
22 | Send Remuneration email to Anupam Sir | Ops | Anirban | 5 | Done
23 | anodiam.com website | Marketing | Debashish | 5 | Done | Develop anodiam.com replicating the above https://www.google.business.anodiam.site
24 | Integration with Class plus website / app login | Marketing | Debashish | 5 | Done | Ask Classplus about the URL / hyperlink for anodiam web app login / register
25 | Sayan and Anupam Sir Bank details | Ops | Debashish | 5 | Done
26 | Batch start for Priyangsu Giri BBA Sem 1 | Ops | Debashish | 5 | Done | Ops Sheet by Debasish Da
27 | Make a Google calander | Marketing | Rahul | 5 | Done
28 | New email ID for Rahul and Sayan. Possible gmail group | Marketing | Sayan | 5 | Done
29 | Prepare generic attachment proposals for schools: Notice | Marketing | Sayan | 5 | Done
30 | Prepare generic attachment proposals for colleges: Notice | Marketing | Sayan | 5 | Done
31 | New student attendance for Manju Ray's son | Ops | Debashish | 5 | Done
32 | Classplus: Website first screen not responsive | Marketing | Debashish | 5 | Done | Sent mail to class plus. Waiting for reply.
33 | Classplus: Login page appearing twice, is this a cache problem? How to sort this? | Marketing | Debashish | 5 | Done | Sent mail to class plus. Waiting for reply.
34 | Classplus: Anodiam Branding absent | Marketing | Debashish | 5 | Done | Sent mail to class plus. Waiting for reply.
35 | CAT Batch Start | Ops | Rahul | 3 | Done
36 | Update description of status in AI marketing sheet | Marketing | Debashish | 5 | WIP

## Website-Tracker
SlNo | Item Description | Type | Owned by | Priority | Status | Comments
1 | Images & Logos | Marketing | Sayan | 5 | Todo
2 | Videos, Youtube content. Create an youtube channel and start putting in our contents | Marketing | Sayan | 5 | Todo
3 | Fonts (Oxygen) and font sizes | Marketing | Sayan | 5 | Todo
4 | Color schemes (RGBA values) of each component | Marketing | Sayan | 5 | Todo
5 | Hyperlinks and Button Click Events including whatsapp integration | Marketing | Sayan | 5 | Todo
6 | Texts and headings (verbose properly / a lot is already there in ppts already) | Marketing | Sayan | 5 | Todo
7 | About Us & Service should have AI Junior & Robotics | Marketing | Sayan | 5 | Todo
8 | About Us & Service should have AI Professional & IT | Marketing | Sayan | 5 | Todo
9 | About Us & Service should have other Swim lanes (You may want to avoid this for now) | Marketing | Sayan | 5 | Todo
10 | Ensure we have a button to download anodiam app from google playstore if anodiam app is not already installed | Marketing | Sayan | 5 | Todo
11 | Ensure we have a button to Use onclick event of same button to open anodiam app if it is already installed | Marketing | Sayan | 5 | Todo
12 | Test the responsiveness of https://www.google.business.sample.site | Marketing | Sayan | 5 | Todo
13 | Must have a button "Visit anodiam.com website": upon clicking it will open anodiam.com >> classplus/YOWWA website | Marketing | Sayan | 5 | Todo

## Antech-Issues
SlNo | Item Description | Type | Owned by | Priority | Status | Comments
1 | The inside & outside photo (360 degree) of our institute should be proper with banners and no blury images | Marketing | Antech | 5 | Done
2 | Address of our institute should be : N 1/25, Kunal Road,Patuli, Kolkata - 700094 | Marketing | Antech | 5 | Done
3 | Opening Hours should be 10 AM to 7 PM. | Marketing | Antech | 5 | Done
4 | In Appointments: wa.me area, there should be whats app icon. | Marketing | Antech | 5 | WIP
5 | Get some 5 star reviews | Marketing | Antech | 5 | WIP
6 | On pressing Website button the page should redirect to google.anodiam.mybusiness.site | Marketing | Antech | 5 | Todo
7 | Search strings to be given to Anttech: NEET IIT institute in Kolkata - AI courses in Kolkata - IT Courses in Kolkata | Marketing | Antech | 5 | Todo

## MockTest
SlNo | Items | Type | Owner | Status | Comments
1 | Mock test Dry run | Mock Test | Debashish | Todo | Final Dry Run by
2 | Mock Test Question Paper | Mock Test | Rahul | Todo | Debashish To Help in technology, Rahul to download & curate soft copies of question bank
3 | Mock Test Presentation | Mock Test | Rahul | Todo | Debashish To Help
4 | Mock test schedule | Mock Test | Anirban | WIP | Monday EOD
5 | Flow chart for Mock Test | Mock Test | Ananya | WIP | by 28/11/2023
6 | Scanned PDF for Mock test, Waqr to confirm | Mock Test | Rahul | Todo | by 28/11/2023
7 | What will be the exact tests (class, board, subjects) for the incumbent / interested students? | Mock Test
8 | Is schedule ready for all the prospective students according to their class / board / subjects? | Mock Test
9 | Who will be the faculty for each test on each date and time? (Get consent from the faculty on availability) | Mock Test
10 | Who will lead the team on each day and each test? | Mock Test
11 | What team members will be supporting the tests for admin work? Who will do what? | Mock Test
12 | What team members will be supporting the tests for Marketing work / presentation? Who will do what? | Mock Test
13 | Is faculty ready with demo class? How will faculty raise interest of the students on the topic of her/his demo class. Will the question paper pattern be hard for these chapters? | Mock Test
14 | Does faculty have soft copies of class notes / presentations / points to remember / sample questions etc. to be displayed in the demo class? | Mock Test
15 | Can the faculty / team show the apps (class plus / college doors) as points of competencies during the presentation after mock test? | Mock Test
16 | Is the demo class rehearsed? | Mock Test
17 | Is the marketing / counselling / presentation rehearsed? | Mock Test
18 | What is the question paper pattern for the test as per board / class/ subject? (Time limit, number of questions , full marks, marks per question / sections, questions covering entire syllabus, question type (MCQ, objective, descriptive etc) | Mock Test
19 | Is the question paper reviewed? | Mock Test
20 | Do we have answering instructions / sample answers ready? | Mock Test
21 | Wich chapters will students will find easy / scoring, which ones difficult? Are we designing demo class around the critical ones? | Mock Test
22 | Is each team member aware of all the above points? | Mock Test
23 | what will be the start time and end time of tests? | Mock Test
24 | Which room will the students sit? | Mock Test
25 | Which room will the parents sit? | Mock Test
26 | Which toilet, water dispenser, facilities, parking, tea coffee etc… | Mock Test
27 | Where will other BAU go during Mock tests? | Mock Test
28 | How we manage invigilation? | Mock Test
29 | How we manage parent's expectation? | Mock Test
30 | Will the parents attend demo class? | Mock Test
31 | Will counselling be in groups or individual? | Mock Test
32 | Is counselling strategy defined? | Mock Test
33 | What will be the course fees for each subject / board / test? Will we provide discounts? Is this as per profitability? | Mock Test
34 | Which faculty will be appointed for each students upon enrollment? Is that faculty aware? Is she the same one conducting the test? | Mock Test
35 | How do we manage expectations and volatile / unrully behavior of students and parents? Are team members aware of all these? | Mock Test
36 | How do we invite students for the consecutive mock tests? | Mock Test
37 | How do we show them a career path for individual students during counselling? | Mock Test
38 | How do we ensure all students / parents / faculty and team members leave in a positive note? | Mock Test
39 | Are we aware of App functionalityies for each test? | Mock Test
40 | Will the students get question papers on laptops / mibile phones? Or papers? If online, did we ask them to bring laptops / mobiles? Will we give them wifi access? | Mock Test
41 | If tests are online how do we manage disruptions due to FB and other websites on the same device? | Mock Test
42 | How we collect phone numbers and contact info of parents / students? | Mock Test
43 | How do we manage CRM with each one after mock tests? | Mock Test
44 | Are we ready with a ppt about Anodiam and why they enroll with us? Who will deliver the presentation? When? Is it reharsed? | Mock Test
45 | Do we ask clients to join a FB / WA group? Is that group a generic one or something specific for particular subject / board / class? | Mock Test
46 | How do we cross sale other subjects to them? How do we ask them to refer other students? How do we ask them to do AI and Communication classes? | Mock Test
47 | will we send street directions / locations to the parents? Will they assemble 15 mins early? | Mock Test
48 | Will we put up internal branding during mock test (Standies / leaflets)? | Mock Test
49 | Will ge need signages inside the building? | Mock Test
50 | Seating arrangements? | Mock Test
51 | Cleaning services and housekeeping? | Mock Test
52 | Define a sequence / timeline of key activities for mock test | Mock Test
53 | Dry run a mock test end to end as per the above equence / timeline of key activities | Mock Test

## WorkDays
Names | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Anirban Chakrabarty | Working | Working | Working | Working | Working | Working | Working
Debasish Nath | Working | Working | Off | Working | Working | Working | Working
Ananya Moitra | Working | Working | Working | Working | Working | Working | Working
Rahul Dutta | Working | Working | Off | Working | Working | Off | Working
Shayan Basak | Off | Working | Working | Working | Working | Off | Off

## Notes
1. Design the corresponding components for https://www.google.business.anodiam.site
A. Images & Logos
B. Videos, Youtube content. Create an youtube channel and start putting in our contents
C. Fonts (Oxygen) and font sizes
D. Color schemes (RGBA values) of each component
E. Hyperlinks and Button Click Events including whatsapp integration
F. Texts and headings (verbose properly / a lot is already there in ppts already)
G. About Us & Service should have following sections:
i. AI Junior & Robotics
ii. AI Professional & IT
iii. Other Swim lanes (You may want to avoid this for now)
2. Antech to develop https://www.google.business.anodiam.site using above components
3. Ensure we have a button to:
A. download anodiam app from google playstore if anodiam app is not already installed
B. Use onclick event of same button to open anodiam app if it is already installed
4. Test the responsiveness of https://www.google.business.sample.site
5. Must have a button "Visit anodiam.com website": upon clicking it will open anodiam.com >> classplus/YOWWA website