## Tracker
Item Number | Item Description | Type | Owned by | Priority | Status | Comments | Link
1 | Plan School Visits | Marketing | Rahul | 5 | WIP
2 | Make a Google calander | Marketing | Rahul | 5 | Todo
3 | New email ID for Rahul and Sayan. Possible gmail group | Marketing | Sayan | 5 | Todo
4 | Prepare generic attachment proposals for schools | Marketing | Sayan | 5 | Done
5 | Plan College Visits | Marketing | Sayan | 5 | WIP | Consilidate School and College marketing sheets into one workbook
6 | Prepare Notice board pamphlet template | Marketing | Sayan | 5 | WIP
7 | Prepare generic attachment proposals for colleges | Marketing | Sayan | 5 | Done
8 | CRM calls | CRM | Debashish | 5 | WIP | Check Just Dial daily. Transfer to Urban Pro
9 | Start / config Selenium batch for Ashmita / Pranay | Ops | Debashish | 5 | Todo | Contact Pranay for status update
10 | Reel Plan (Generic Ad) | Digital Marketing | Anirban | 3 | WIP | Need to break this down further
11 | Reel Plan (AI Ad) | Digital Marketing | Anirban | 3 | WIP | Need to break this down further
12 | Google Anttech Photoshhot | Digital Marketing | Sayan | 5 | Todo | Need to Plan
13 | Google Anttech Google business site | Digital Marketing | Debashish | 5 | WIP | 1. Design the corresponding components for https://www.google.business.anodiam.site A. Images & Logos B. Videos, Youtube content. Create an youtube channel and start putting in our contents C. Fonts (Oxygen) and font sizes D. Color schemes (RGBA values) of each component E. Hyperlinks and Button Click Events including whatsapp integration F. Texts and headings (verbose properly / a lot is already there in ppts already) G. About Us & Service should have following sections: i. AI Junior & Robotics ii. AI Professional & IT iii. Other Swim lanes (You may want to avoid this for now) 2. Antech to develop https://www.google.business.anodiam.site using above components 3. Ensure we have a button to: A. download anodiam app from google playstore if anodiam app is not already installed B. Use onclick event of same button to open anodiam app if it is already installed 4. Test the responsiveness of https://www.google.business.sample.site 5. Must have a button "Visit anodiam.com website": upon clicking it will open anodiam.com >> classplus/YOWWA website
14 | anodiam.com website | Digital Marketing | Debashish | 5 | Done | Develop anodiam.com replicating the above https://www.google.business.anodiam.site
15 | Integration with Class plus website / app login | Digital Marketing | Debashish | 5 | Done | Ask Classplus about the URL / hyperlink for anodiam web app login / register
16 | Student fees collection report for December | Ops | Anirban | 5 | WIP | Anirban has to send bank receipt after 8-Jan
17 | Conduct Internal Assessment Test Chem - Avishek - Nov | Ops | Debashish | 5 | WIP | Avishek to complete correction by 30-Dec-2023
18 | Company Income Expense Ledger & Balance Sheet | Ops | Anirban | 5 | Todo | Start in December
19 | News Paper flyers distribution | Marketing | Rahul | 2 | WIP | To start in Feb 4th week
20 | Batch start for Priyangsu Giri BBA Sem 1 | Ops | Debashish | 5 | WIP | Anirban needs to send email about fees to Anupam sir, Rahul to let Anirban know of the exact subject names
21 | AI Internal Classes - Sayan | Ops | Sayan | 3 | Todo | Start from 4-Jan-2024
22 | AI Internal Classes by Anirban | Ops | Anirban | 3 | Todo | Start from 4-Jan-2024
23 | CAT Batch Start | Ops | Rahul | 3 | Todo
25 | Sayan and Anupam Sir Bank details | Ops | Debashish | 5 | Done
26 | New student attendance for Manju Ray's son | Ops | Debashish | 5 | Todo
27 | Classplus: Website first screen not responsive | Marketing | Debashish | 5 | WIP | Sent mail to class plus. Waiting for reply.
28 | Classplus: Login page appearing twice, is this a cache problem? How to sort this? | Marketing | Debashish | 5 | WIP | Sent mail to class plus. Waiting for reply.
29 | Classplus: Anodiam Branding absent | Marketing | Debashish | 5 | WIP | Sent mail to class plus. Waiting for reply.
30 | Create events at meetup app or https://www.townscript.com/ | Rahul | Debashish | 5 | Todo
31 | Publish purchased course materials on Anodiam platform | Ops | Debashish | 4 | Todo

## MockTest
23 | Mock test Dry run | Mock Test | Debashish | Todo | Final Dry Run by
24 | Mock Test Question Paper | Mock Test | Rahul | Todo | Debashish To Help in technology, Rahul to download & curate soft copies of question bank
25 | Mock Test Presentation | Mock Test | Rahul | Todo | Debashish To Help
26 | Mock test schedule | Mock Test | Anirban | WIP | Monday EOD
20 | Flow chart for Mock Test | Mock Test | Ananya | WIP | by 28/11/2023
21 | Scanned PDF for Mock test, Waqr to confirm | Mock Test | Rahul | Todo | by 28/11/2023
28 | What will be the exact tests (class, board, subjects) for the incumbent / interested students? | Mock Test
29 | Is schedule ready for all the prospective students according to their class / board / subjects? | Mock Test
30 | Who will be the faculty for each test on each date and time? (Get consent from the faculty on availability) | Mock Test
31 | Who will lead the team on each day and each test? | Mock Test
32 | What team members will be supporting the tests for admin work? Who will do what? | Mock Test
33 | What team members will be supporting the tests for Marketing work / presentation? Who will do what? | Mock Test
34 | Is faculty ready with demo class? How will faculty raise interest of the students on the topic of her/his demo class. Will the question paper pattern be hard for these chapters? | Mock Test
35 | Does faculty have soft copies of class notes / presentations / points to remember / sample questions etc. to be displayed in the demo class? | Mock Test
36 | Can the faculty / team show the apps (class plus / college doors) as points of competencies during the presentation after mock test? | Mock Test
37 | Is the demo class rehearsed? | Mock Test
38 | Is the marketing / counselling / presentation rehearsed? | Mock Test
39 | What is the question paper pattern for the test as per board / class/ subject? (Time limit, number of questions , full marks, marks per question / sections, questions covering entire syllabus, question type (MCQ, objective, descriptive etc) | Mock Test
40 | Is the question paper reviewed? | Mock Test
41 | Do we have answering instructions / sample answers ready? | Mock Test
42 | Wich chapters will students will find easy / scoring, which ones difficult? Are we designing demo class around the critical ones? | Mock Test
43 | Is each team member aware of all the above points? | Mock Test
44 | what will be the start time and end time of tests? | Mock Test
45 | Which room will the students sit? | Mock Test
46 | Which room will the parents sit? | Mock Test
47 | Which toilet, water dispenser, facilities, parking, tea coffee etc… | Mock Test
48 | Where will other BAU go during Mock tests? | Mock Test
49 | How we manage invigilation? | Mock Test
50 | How we manage parent's expectation? | Mock Test
51 | Will the parents attend demo class? | Mock Test
52 | Will counselling be in groups or individual? | Mock Test
53 | Is counselling strategy defined? | Mock Test
54 | What will be the course fees for each subject / board / test? Will we provide discounts? Is this as per profitability? | Mock Test
55 | Which faculty will be appointed for each students upon enrollment? Is that faculty aware? Is she the same one conducting the test? | Mock Test
56 | How do we manage expectations and volatile / unrully behavior of students and parents? Are team members aware of all these? | Mock Test
57 | How do we invite students for the consecutive mock tests? | Mock Test
58 | How do we show them a career path for individual students during counselling? | Mock Test
59 | How do we ensure all students / parents / faculty and team members leave in a positive note? | Mock Test
60 | Are we aware of App functionalityies for each test? | Mock Test
61 | Will the students get question papers on laptops / mibile phones? Or papers? If online, did we ask them to bring laptops / mobiles? Will we give them wifi access? | Mock Test
62 | If tests are online how do we manage disruptions due to FB and other websites on the same device? | Mock Test
63 | How we collect phone numbers and contact info of parents / students? | Mock Test
64 | How do we manage CRM with each one after mock tests? | Mock Test
65 | Are we ready with a ppt about Anodiam and why they enroll with us? Who will deliver the presentation? When? Is it reharsed? | Mock Test
66 | Do we ask clients to join a FB / WA group? Is that group a generic one or something specific for particular subject / board / class? | Mock Test
67 | How do we cross sale other subjects to them? How do we ask them to refer other students? How do we ask them to do AI and Communication classes? | Mock Test
69 | will we send street directions / locations to the parents? Will they assemble 15 mins early? | Mock Test
70 | Will we put up internal branding during mock test (Standies / leaflets)? | Mock Test
71 | Will ge need signages inside the building? | Mock Test
72 | Seating arrangements? | Mock Test
73 | Cleaning services and housekeeping? | Mock Test
74 | Define a sequence / timeline of key activities for mock test | Mock Test
75 | Dry run a mock test end to end as per the above equence / timeline of key activities | Mock Test

## WorkDays
Names | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Anirban Chakrabarty | Working | Working | Working | Working | Working | Working | Working
Debasish Nath | Working | Working | Off | Working | Working | Working | Working
Ananya Moitra | Working | Working | Working | Working | Working | Working | Working
Rahul Dutta | Working | Working | Off | Working | Working | Off | Working
Shayan Basak | Off | Working | Working | Working | Working | Off | Off