## OpsTracker
Item Number | Item Description | Owned by | Status | Comments | Link
1 | Plan School Visits | Rahul | WIP
2 | Plan Road Shows | Rahul | WIP
3 | College doors app walkthrough to team | Sayan | WIP | Planned for 10-Nov After morning stand-up
4 | Spoken English syllabus compilation | Rahul | WIP
5 | Spoken English training to Victor & Sathi | Rahul | Todo | On Tuesdays
6 | MS Office training | Debashish | WIP | On Tuesdays
7 | Git access & training to Rahul | Anirban | WIP
8 | News Paper flyers distribution | Anirban | WIP
9 | Mock test Dry run | Debashish | Todo
10 | Mock Test Question Paper | Rahul | Todo | Debashish To Help
11 | Mock Test Presentation | Rahul | Todo | Debashish To Help
12 | Mock test schedule | Anirban | WIP | Monday EOD
13 | College doors app defect management | Debashish | WIP | Debashish and Ananya tested from our end and raised 25 defects. We notified College Doors Waqar reverted back and we will check on Monday (20th November 2023)
14 | Reel Plan (Generic Ad) | Rahul | WIP
15 | Reel Plan (AI Ad) | Rahul | WIP
16 | Google anttech pay and deploy personel | Rahul | Todo
17 | Google Anttech Photoshhot | Rahul | Todo
18 | Google Anttech Google Landing Page | Rahul | Todo
19 | Student fees collection report | Debashish | WIP | Fees Collection report done.Java Student Batch creation left in ClassPlus APP
20 | ID card for all | Victor | WIP | Photo shoot of Sathi and Victor is done. Sayan and Rahul still yet to give photo to Anirban
21 | Conduct Internal Assessment Test Chem | Debashish | WIP | Subroto Sir will set Question paper by Thursday (23-11-2023)
22 | Conduct Internal Assessment Test Physics | Debashish | WIP | Talk to Avishek Sir
23 | Company Income Expense Ledger & Balance Sheet | Anirban | Todo
24 | File for daily visit enquiry Sheet | Rahul | Todo | New File to be purchased
25 | File for bio data of teacher | Rahul | Todo | Already file is there, we need to remove other documents from this file
26 | Online interview of Pronay Dhargave on 16 Nov at 3 PM | Debashish | WIP | Prannay is selected. His biodata and other credentials needed to be taken.

## WorkDays
Names | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Anirban Chakrabarty | Working | Working | Working | Working | Working | Off | Off
Debasish Nath | Off | Working | Working | Working | Working | Working | Working
Ananya Moitra | Working | Working | Working | Working | Working | Off | Off
Shayan Basak | Working | Working | Working | Working | Working | Off | Off
Charles Victor Roy | Working | Working | Working | Off | Working | Working | Off
Rahul Dutta | Working | Working | Off | Working | Working | Off | Working
Sathi Das | Working | Working | Off | Working | Off | Off | Off

## InternalAdmin
Item Number | Item | Status | Owner
1 | Furniture Repairing | WIP | Victor
2 | Banking issue (HDFC Vyapar Transaction Summary & Net Banking) | WIP | Anirban
3 | ID card jacket purchase | Todo | Anirban
4 | Three Mirrors. 1.5 Foot By 2 Foot | Todo | Anirban
5 | Switch Repair Kitchen | Todo | Anirban
6 | Light Point at Staircase | Todo | Anirban
7 | Tissue Paper dispensor at Bathroom in Ist Floor | Todo | Anirban