## Tracker
SlNo | Item Description | Type | Owned by | Priority | Status | Comments | Link
1 | Plan School and College Visits | Marketing | Rahul | 5 | WIP | Pending on Anttech business site, Email body shortened and rectified, Institution Full name left
2 | Close UAT Defects of Anodiam Business Site | Ops | Anirban | 5 | WIP
3 | Get some 5 star reviews | Marketing | Sayan | 5 | Todo
4 | Search strings to be given to Anttech: NEET IIT institute in Kolkata - AI courses in Kolkata - IT Courses in Kolkata | Marketing | Sayan | 5 | Todo
5 | Videos, Youtube content. Create an youtube channel and start putting in our contents | Marketing | Anirban | 5 | Todo
6 | Write full names of institutions for Emails | Marketing | Rahul | 5 | Todo
7 | Create Subdomain for login into classplus app | Marketing | Anirban | 5 | Todo
8 | Download Anttech business site source code and upload it to anodiam.com domain | Marketing | Anirban | 5 | Todo
9 | Create generic Thumbnail (Coverpage) image / ppt for courses | Ops | Sayan | 4 | WIP
10 | AI Internal Classes - Sayan | Ops | Sayan | 4 | WIP | Start from 5-Feb-2024
11 | Communication - Internal Classes | Ops | Rahul | 4 | WIP | Plan the table of contents for the syllabus
12 | AI Internal Classes by Anirban | Ops | Anirban | 4 | WIP | Start from 4-Jan-2024
13 | Publish AI & Java course materials on Anodiam platform | Ops | Sayan | 4 | WIP | PPTs only for now at version 0.0.1. Debasish da to work on Java Materials
14 | Create a detailed syllabus for communication | Marketing | Rahul | 4 | WIP
15 | CRM calls: Just dial to Urban Pro: | CRM | Rahul | 3 | WIP | Check Just Dial daily. Transfer to Urban Pro. Just Dial email Id : kolkata@justdial.com. After 5th Feb.
16 | Write email to stop just dial | CRM | Anirban | 5 | Todo
17 | Reel Plan (AI Ad) | Marketing | Anirban | 3 | Todo | Need to break this down further
18 | Reel Plan (Generic Ad) | Marketing | Anirban | 3 | Todo | Need to break this down further
19 | Start / config Selenium batch for Ashmita / Pranay | Ops | Rahul | 3 | WIP | Pranay has been updated.
20 | News Paper flyers distribution | Marketing | Rahul | 2 | WIP | To start in Feb 4th week