## ToDoList-16-12-2023
Slno | Items | Status | Remarks
1 | Call Bappa for discussion of demo on 16-12-2023 | Done
2 | Get a maid for cleaning the demo room | Done | On 15-12-2023 morning, one cleaner will come and clean the demo room,bathroom,stair case and other rooms
3 | Clean the demo room on the 2nd floor | Done
4 | Make a separate list of students for demo | Done | 11 sudents has been listed
5 | Get the different accessories like table or chair to decorate the room for demo | Done
6 | Rahul needed to call gurdian Madhuparna acharya to confirm. | Done | Will join after March
7 | Keep the toys and other accessories inside the demo room | Not-Done | Bappa will bring the toys on 16-12-2023 (Saturday). He did not able to come on 14-12-2023
8 | Make the required signages for demo room | Not-Done | Anirban will print signages tommorow (16-12-2023).
9 | Install the CCTV camera inside the demo room | Done
10 | Paste different posters for children in the demo room | Done
11 | Place a standie in the entrance for demo date 16 Dec 2023 | Not-Done | Sayan will put standie on 16-12-2023
12 | Make a stock for tea,coffee,buiscuits for demo date 16 Dec 2023 | Done
13 | Complete the anodiam website | In-Progress | To be done later.
14 | Deploy the anodiam website | In-Progress
15 | Call Hiya for 16th Dec demo | Done
16 | Fix the TV | Done
17 | Fix the white board in the demo room for 16 Dec 2023 | Done
18 | Clean the bathroom of demo room for 16 Dec 2023 | Done
19 | Sayan to create slide for presentation | In-Progress | 1 slide left
20 | Slides for Bappa (We need to create for him) | Done
21 | Slides for Avishek (We need to create for him) | Done
22 | Slides for Rahul | Done
23 | Reahersal for demo by speakers with slides on 16-12-2023 | Not-Done | All the speakers needed to do reahersal in the morning hours of 16-12-2023
24 | Door coloring by carpenter | Done
25 | 3 bulbs needed to purchase for demo room and to fix the bulbs | Done
26 | Anirban to create slide for presentation | In-Progress

## Expense-For-16-12-2023
SlNo | Expense Head | Amount
1 | Chair Repair Expense | 250
2 | 15 W Bulbs (3) | 450
3 | Painting Of Doors | 900
4 | Building Cleaning | 1000
| Total | 2600

## Students-For-Demo-16-12-2023
Slno | Student Name | Student's Phone No | Gurdian Name | Gurdian's Phone No | School Name | Address | Reference | Class | Remarks (In Comments)
1 | Rounak Bhattacharya |  | Piyali Bhattacharya | 9123029764 |  | Jadavpur | Anirban Chakraborty
2 |  |  | Nipun Saha | 9883359259 |  | Garia | Anirban Chakraborty
3 |  |  | Amrita | 9038840453 |  | Garia | Anirban Chakraborty
4 | Kalyani Sarkar | 8336817657 |  |  |  | Patuli Locality
5 | Jyoti |  |  | 7278448048 |  | Patuli Locality
6 | Suvomita |  | Goutam Das | 9830826860 |  | Patuli Locality
7 | Sumita | 6294268223 |  |  |  | Patuli Locality
8 |  |  | Monaranjan Das | 9433055625 |  | Patuli Locality
9 |  |  | Jhuma | 8016981657 |  | Patuli Locality
10 | Suvangihi | 7596825771 |  |  |  | Patuli Locality
11 | Suvangihi's Brother | 7596825771 |  |  |  | Patuli Locality

## Speakers-16-12-2023
SlNo | Speakers | Topics
1 | Sayan Basak | AI/ML Foundation
Coding Core
2 | Bappaditto | Robotics | Demo of robotic car. Explanation of circuit,adriano. 7 segment display.
|  | IOT | How robotics fit in their career ?
3 | Avishek Adhikari | Vedic Maths
Mental Maths
4 | Srijina Mukherjee | Communication Skills
Social Intelligence
5 | Rahul Dutta | Communication Skills
Social Intelligence