## OpsTracker
Item Number | Item Description | Owned by | Status | Comments | Link
1 | Plan School Visits | Victor | WIP
2 | Plan Road Shows | Victor | WIP
3 | College doors app walkthrough to team | Sayan | WIP | Planned for 10-Nov After morning stand-up
7 | Spoken English syllabus compilation | Rahul | WIP
8 | Spoken English training to Victor & Sathi | Rahul | Todo | On Tuesdays
9 | MS Office training | Debashish | WIP | On Tuesdays
11 | Git access & training to Rahul | Anirban | WIP
12 | News Paper flyers distribution | Anirban | WIP
13 | Stamp Pad | Victor | WIP
14 | Initial College doors Mock test Dry run | Debashish | Done | Debashish and Ananya tested from our end and raised 25 defects. We notified College Doors
15 | College doors app defect management | Debashish | WIP | Waqar reverted back and we will check on Monday (20th November 2023)
16 | Reel Plan (Generic Ad) | Rahul | WIP
17 | Reel Plan (AI Ad) | Rahul | WIP
18 | Google anttech pay and deploy personel | Anirban | Todo
19 | Google Anttech Photoshhot | Debashish | Todo
20 | Google Anttech Google Landing Page | Debashish | Todo
22 | Student fees collection report | Debashish | WIP | Fees Collection report done.Java Student Batch creation left in ClassPlus APP
25 | ID card for all | Victor | WIP
26 | Merch for Marketing Team | Anirban | WIP | Return of Merch (Debashish and Sayan)
27 | Conduct Internal Assessment Test for existing Students: Questions needed to type from JELETE Book for internal Chemistry test on 30th November | Debashish | WIP | Why cannot teacher's type the question papers?
|  | Debashish | WIP | We communicated to Subroto Sir. He will do the necessary stuffs on Thursday (23-11-2023)
28 | Company Income Expense Ledger & Balance Sheet | Anirban | Todo
29 | File for daily visit enquiry Sheet | Rahul | Todo | New File to be purchased
30 | File for bio data of teacher | Rahul | Todo | Already file is there, we need to remove other documents from this file
32 | Online interview of Pronay Dhargave on 16 Nov at 3 PM | Debashish | Done | Prannay is selected.
33 | Start building up Mock Test Question Paper | Rahul | Todo | Debashish To Help
34 | Start building up Mock Test Presentation | Rahul | Todo | Debashish To Help
35 | Mock test schedule | Anirban | WIP | Monday EOD
36 | Dry run of Mock Test with 3 users | Debashish | Todo | On 20th November 2023, we will test with 3 users

## WorkDays
Names | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Anirban Chakrabarty | Working | Working | Working | Working | Working | Off | Off
Debasish Nath | Working | Working | Working | Off | Working | Working | Working
Ananya Moitra | Working | Working | Working | Working | Working | Off | Off
Shayan Basak | Working | Working | Working | Working | Working | Off | Off
Charles Victor Roy | Working | Working | Working | Off | Working | Working | Off
Rahul Dutta | Working | Working | Off | Working | Working | Off | Working
Sathi Das | Working | Working | Off | Working | Off | Off | Off

## InternalAdmin
Item Number | Item | Status | Owner
1 | Furniture Repairing | WIP | Victor
2 | Banking issue (HDFC Vyapar Transaction Summary & Net Banking) | WIP | Anirban
3 | ID card jacket purchase | Todo | Anirban
5 | Three Mirrors. 1.5 Foot By 2 Foot | Todo | Anirban
6 | Phenyl | Todo | Anirban
7 | Switch Repair Kitchen | Todo | Anirban
8 | Light Point at Staircase | Todo | Anirban
9 | Tissue Paper dispensor at Bathroom in Ist Floor | Todo | Anirban
10 | Wet Tissue | Todo | Anirban
11 | Coffee | Todo | Anirban
12 | Tea | Todo | Anirban
13 | Powder milk | Todo | Anirban