## OpsTracker
Item Number | Item Description | Owned by | Status | Comments | Link
1 | Plan School Visits | Rahul | WIP
2 | Plan Road Shows | Rahul | WIP
3 | Spoken English syllabus compilation | Rahul | WIP | Anirban to review
4 | Spoken English training to Victor & Sathi | Rahul | Todo | On Tuesdays
5 | MS Office training | Debashish | WIP | On Tuesdays
6 | News Paper flyers distribution | Anirban | WIP
7 | Reel Plan (Generic Ad) | Rahul | WIP
8 | Reel Plan (AI Ad) | Rahul | WIP
9 | Google anttech pay and deploy personel | Rahul | Todo
10 | Google Anttech Photoshhot | Rahul | Todo
11 | Google Anttech Google Landing Page | Rahul | Todo
12 | Student fees collection report | Debashish | WIP | Fees Collection report done.Java Student Batch creation left in ClassPlus APP
13 | ID card for all | Victor | WIP | Photo shoot of Sathi and Victor is done. Sayan and Rahul still yet to give photo to Anirban
14 | Conduct Internal Assessment Test Chem | Debashish | WIP | Subroto Sir will set Question paper by Thursday (23-11-2023)
15 | Conduct Internal Assessment Test Physics | Debashish | WIP | Talk to Avishek Sir
16 | Company Income Expense Ledger & Balance Sheet | Anirban | Todo
17 | File for daily visit enquiry Sheet | Rahul | Todo | New File to be purchased
18 | File for bio data of teacher | Rahul | Todo | Already file is there, we need to remove other documents from this file
19 | Online interview of Pronay Dhargave on 16 Nov at 3 PM | Debashish | WIP | Prannay is selected. His biodata and other credentials needed to be taken.
20 | Flow chart for Mock Test | Ananya | WIP | by 22/11/2023
21 | Scanned PDF for Mock test, Waqr to confirm | Rahul | Todo | by 21/11/2023
22 | College doors app walkthrough to team | Sayan | WIP | Planned for 10-Nov After morning stand-up
23 | Mock test Dry run | Debashish | Todo
24 | Mock Test Question Paper | Rahul | Todo | Debashish To Help in technology, Rahul to download & curate soft copies of question bank
25 | Mock Test Presentation | Rahul | Todo | Debashish To Help
26 | Mock test schedule | Anirban | WIP | Monday EOD
27 | College doors app defect management | Debashish | WIP | Debashish and Ananya tested from our end and raised 25 defects. We notified College Doors Waqar reverted back and we will check on Monday (20th November 2023)
28 | What will be the exact tests (class, board, subjects) for the incumbent / interested students?
29 | Is schedule ready for all the prospective students according to their class / board / subjects?
30 | Who will be the faculty for each test on each date and time? (Get consent from the faculty on availability)
31 | Who will lead the team on each day and each test?
32 | What team members will be supporting the tests for admin work? Who will do what?
33 | What team members will be supporting the tests for Marketing work / presentation? Who will do what?
34 | Is faculty ready with demo class? How will faculty raise interest of the students on the topic of her/his demo class. Will the question paper pattern be hard for these chapters?
35 | Does faculty have soft copies of class notes / presentations / points to remember / sample questions etc. to be displayed in the demo class?
36 | Can the faculty / team show the apps (class plus / college doors) as points of competencies during the presentation after mock test?
37 | Is the demo class reharsed?
38 | Is the marketing / counselling / presentation reharsed?
39 | What is the question paper pattern for the test as per board / class/ subject? (Time limit, number of questions , full marks, marks per question / sections, questions covering entire syllabus, question type (MCQ, objective, descriptive etc)
40 | Is the question paper reviewed?
41 | Do we have answering instructions / sample answers ready?
42 | Wich chapters will students will find easy / scoring, which ones difficult? Are we designing demo class around the critical ones?
43 | Is each team member aware of all the above points?
44 | what will be the start time and end time of tests?
45 | Which room will the students sit?
46 | Which room will the parents sit?
47 | Which toilet, water dispenser, facilities, parking, tea coffee etc…
48 | Where will other BAU go during Mock tests?
49 | How we manage invigilation?
50 | How we manage parent's expectation?
51 | Will the parents attend demo class?
52 | Will counselling be in groups or individual?
53 | Is counselling strategy defined?
54 | What will be the course fees for each subject / board / test? Will we provide discounts? Is this as per profitability?
55 | Which faculty will be appointed for each students upon enrollment? Is that faculty aware? Is she the same one conducting the test?
56 | How do we manage expectations and volatile / unrully behavior of students and parents? Are team members aware of all these?
57 | How do we invite students for the consecutive mock tests?
58 | How do we show them a career path for individual students during counselling?
59 | How do we ensure all students / parents / faculty and team members leave in a positive note?
60 | Are we aware of App functionalityies for each test?
61 | Will the students get question papers on laptops / mibile phones? Or papers? If online, did we ask them to bring laptops / mobiles? Will we give them wifi access?
62 | If tests are online how do we manage disruptions due to FB and other websites on the same device?
63 | How we collect phone numbers and contact info of parents / students?
64 | How do we manage CRM with each one after mock tests?
65 | Are we ready with a ppt about Anodiam and why they enroll with us? Who will deliver the presentation? When? Is it reharsed?
66 | Do we ask clients to join a FB / WA group? Is that group a generic one or something specific for particular subject / board / class?
67 | How do we cross sale other subjects to them? How do we ask them to refer other students? How do we ask them to do AI and Communication classes?
69 | will we send street directions / locations to the parents? Will they assemble 15 mins early?
70 | Will we put up internal branding during mock test (Standies / leaflets)?
71 | Will ge need signages inside the building?
72 | Seating arrangements?
73 | Cleaning services and housekeeping?

## WorkDays
Names | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Anirban Chakrabarty | Working | Working | Working | Working | Working | Off | Off
Debasish Nath | Off | Working | Working | Working | Working | Working | Working
Ananya Moitra | Working | Working | Working | Working | Working | Off | Off
Shayan Basak | Working | Working | Working | Working | Working | Off | Off
Charles Victor Roy | Working | Working | Working | Off | Working | Working | Off
Rahul Dutta | Working | Working | Off | Working | Working | Off | Working
Sathi Das | Working | Working | Off | Working | Off | Off | Off

## InternalAdmin
Item Number | Item | Status | Owner
1 | Furniture Repairing | WIP | Victor
2 | Banking issue (HDFC Vyapar Transaction Summary & Net Banking) | WIP | Anirban
3 | ID card jacket purchase | Todo | Anirban
4 | Three Mirrors. 1.5 Foot By 2 Foot | Todo | Anirban
5 | Switch Repair Kitchen | Todo | Anirban
6 | Light Point at Staircase | Todo | Anirban
7 | Tissue Paper dispensor at Bathroom in Ist Floor | Todo | Anirban