## OpsTracker
Item Number | Item Description | Owned by | Status | Comments | Link
1 | Make Spreadsheet for Weekly off of team members | Rahul | Done
2 | Plan School Visits | Victor | WIP
3 | Plan Road Shows | Victor | WIP
4 | College doors app walkthrough to team | Sayan | WIP | Planned for 10-Nov After morning stand-up
5 | Classplus app walkthrough to team | Sayan | WIP | Planned for 14-Nov After morning stand-up
6 | CRM walkthrough to team | Debasish | Todo
7 | Marketing Materials reverse KT | Rahul | WIP
8 | Spoken English syllabus compilation | Rahul | WIP
9 | Spoken English training to Victor | Rahul | Todo
10 | MS Office self training | Victor | WIP | Aniban to review the training plan by 10-Nov
11 | Teaching Ops training to team | Anirban | Done
12 | Git access & training to Rahul & Victor | Anirban | Todo
13 | News Paper flyers distribution | Anirban | WIP
14 | Marketing KT to Rahul | Victor | Done
15 | Stamp Pad | Anirban | Done
16 | College doors student journey KT by Waqar | Debasish | Todo
17 | College doors app defect management | Debasish | WIP
18 | Reel Plan (Generic Ad) | Rahul | WIP
19 | Reel Plan (AI Ad) | Rahul | WIP
20 | Google Anttech Photoshhot | Debasish | Todo
21 | Google Anttech Google Landing Page | Debasish | Todo
22 | Admin Activities sheet | Victor | Done
23 | Student fees collection report | Anirban | WIP | Java Student Batch creation left
24 | Teacher payout slip prepare | Anirban | WIP | Debasish Sir left
25 | Teacher payout Excel | Anirban | WIP | Debasish Sir left
26 | ID card for all | Anirban | WIP
27 | Merch for Marketing Team | Anirban | WIP
28 | Buy JELET Book | Debasish | Todo
29 | Conduct Internal Assessment Test for existing Students | Debasish | Todo

## WorkDays
Names | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Anirban Chakroborty | Working | Working | Working | Working | Working | Off | Off
Debasish Nath | Working | Working | Working | Off | Working | Working | Working
Ananya Moitra | Working | Working | Working | Working | Working | Off | Off
Shayan Basak | Working | Working | Working | Working | Working | Off | Off
Charles Victor Roy | Working | Working | Working | Off | Working | Working | Off
Rahul Dutta | Working | Working | Off | Working | Working | Off | Working
Sathi Das | Working | Working | Off | Working | Off | Off | Off

## InternalAdmin
Item Number | Item | Status | Owner
1 | Furniture Repairing | Todo | Victor
2 | AC Service | Todo | Victor
3 | Internet Issue | WIP | Anirban
4 | Internet Bill | Todo | Anirban
5 | Banking issue (HDFC Vyapar Transaction Summary & Net Banking) | Todo | Anirban
6 | Biscuits | Done | Victor
7 | Electric Bill | Done | Anirban
8 | Pujo Subscription | Todo | Anirban